## Executive Summary
Akasha Delivery Tracker Refresh
Client-facing phase/module tracker aligned to the current Akasha implementation, EOSDA baseline functionality, and active Bhoonidhi ResourceSat work.
Status | Roadmap Rows | Meaning | Current Implementation Snapshot
Done | 3 | Implemented foundations and ready product surfaces. | Basemap | ArcGIS/Esri remains the visual basemap; ResourceSat FCC is overlay-only.
Validated | 2 | Staging/Coolify or real Bhoonidhi validation completed. | Ready screen | Field Analytics / MapPage is the main implemented product workspace.
In Progress | 4 | Active ResourceSat/Bhoonidhi and source-neutral work. | Validated | Coolify staging and Bhoonidhi diagnostic were validated from the staging VM.
Partial | 10 | Backend or UI exists but EOS parity is incomplete. | Active work | ResourceSat source-neutral masks, COG prep, full-AOI composites and sync.
Planned | 5 | Scoped future modules. | EOS baseline | Public EOSDA user guide, especially Seasonality and related modules.
Deferred | 3 | Blocked by external provider/access decision.
Owners
Role | Owner | Primary Scope | Baseline Sources
Frontend | Rafiq | SPA screens, map interactions, EOS-parity UI | Seasonality guide | https://eos.com/user-guide/crop-monitoring/seasonality/
Backend/API | Sanoj | BFF, auth, product APIs, analytics contracts | Add field guide | https://eos.com/user-guide/crop-monitoring/add-field/
Fullstack | Deva | Data workflows, integrations, UI/API joins | Monitoring guide | https://eos.com/user-guide/crop-monitoring/fields/
Architect / Fullstack / DevOps | Nishanth | Architecture, DevOps, Coolify, ingestion orchestration | VRA maps guide | https://eos.com/user-guide/crop-monitoring/vra-maps/
|  |  | Field manager guide | https://eos.com/user-guide/crop-monitoring/field-manager/

## Delivery Roadmap
Phase | Module | EOS Baseline Feature | Akasha Scope | UI Scope | Backend/Data Scope | DevOps/QA Scope | Owner | Priority | Status | Acceptance Criteria | Dependencies | Notes
Phase 0 - Implemented Foundation | Architecture and service topology | Production application foundation | Canonical multi-service app with one public web gateway, internal API/TiTiler/STAC/PostGIS/MinIO, local Docker, Railway, and Coolify portability. | React/Vite SPA served through Caddy gateway; same-origin /api and /tiles paths. | FastAPI BFF, pgSTAC/STAC, PostGIS, MinIO, TiTiler display tile path, ingestion worker. | Docker Compose, health checks, slice validators, smoke test, pinned images. | Architect / Fullstack / DevOps - Nishanth | P0 | Done | Gateway is the only public service; API and tile calls stay same-origin; local stack can bootstrap with make dev. | None. | Old root preview shims are no longer source of truth.
Phase 0 - Implemented Foundation | Auth, teams, account and API access shell | Team Management; Settings; Access Through API | Hand-rolled cookie-session auth with team roles, account profile, API keys, notifications, password change, bootstrap controls. | Login page, auth gate, app shell, account/API/notifications pages. | Auth/session tables, HMAC session tokens, Argon2 password hashing, owner/admin/member/viewer roles, account routes. | Auth-on deployment guardrails; local disabled mode only where permitted. | Backend/API - Sanoj | P0 | Done | Protected routes require session/team context; bootstrap is controlled; API keys never expose service secrets. | Production secrets and password pepper. | Not Better Auth; current implementation is Akasha-owned.
Phase 0 - Implemented Foundation | Core field and plot management | Add field; Draw field; Upload fields; Field Manager | Named plots/fields with geometry, area, crop metadata, season label, groups, import/export. | Field analytics map supports drawing/editing with Terra Draw; field list/panel; GeoJSON import/export actions. | Plot CRUD, field CRUD, field groups, field seasons/seasons models, GeoJSON validation/export. | API tests for plots, fields, field groups, seasons, exports. | Frontend - Rafiq; Backend/API - Sanoj | P0 | Partial | User can create and manage field boundaries through native APIs; EOS-style upload formats beyond GeoJSON remain planned. | Shapefile/KML/KMZ upload parser for full EOS parity. | Current geometry upload is GeoJSON-oriented.
Phase 0 - Implemented Foundation | Map and monitoring workspace | Work With Crop Map; Monitoring; Image sources; Date line; Vegetation indices | MapLibre workspace with ArcGIS basemap, satellite overlays, source/date layer panel, opacity, visibility, compare, measurement, command palette, index panel. | Field Analytics route is the main ready product screen; MapPage drives map, layers, timeline controls, draw/edit, stats panel. | BFF product routes for config, sources, dates, layers, tiles, and index statistics. | Frontend unit tests cover layer/date behavior and same-origin tile URL helpers. | Frontend - Rafiq | P0 | Done | Default map is true-colour basemap; overlay metadata comes from BFF; browser never receives MinIO/STAC/TiTiler internals. | Dense ResourceSat composite catalog for production data. | ArcGIS remains basemap; ResourceSat FCC is an overlay.
Phase 0 - Implemented Foundation | CI/CD and self-hosted deployment | Production operations foundation | GitHub Actions CI, GHCR image build, Coolify staging deploy, production deploy workflow, Azure VM staging validation. | No direct UI feature; deploys the SPA/gateway image. | Builds web/api/ingestion-worker/ingestion-sar images; patches Coolify compose with immutable SHA. | CI runs API tests, frontend lint/test/build, slice validators, Trivy scan; staging deploy uses self-hosted runner. | Architect / Fullstack / DevOps - Nishanth | P0 | Validated | Staging stack can be patched/deployed through Coolify; private service ports remain closed; smoke checks pass. | Production Coolify service UUID and final domain/TLS before production cutover. | Production deploy uses previously validated Git SHA only.
Phase 1 - Bhoonidhi ResourceSat Completion | Bhoonidhi access and product diagnostics | Image sources; monitoring data availability | Validated ResourceSat-2A LISS-3 BOA search/download from staging VM and inspected real product layout. | Admin-only diagnostic result is backend-facing; no raw download exposed in UI. | Bhoonidhi diagnostic endpoint, stdlib client, real download inspection, sanitized job status. | Staging smoke from whitelisted egress IP 20.219.3.35; tests mock network and archive inspection. | Backend/API - Sanoj; Architect / Fullstack / DevOps - Nishanth | P0 | Validated | Search returns Online=Y products; download succeeds; product contains BAND2/BAND3/BAND4/BAND5; no native quality raster found. | Bhoonidhi credentials and static staging egress must remain valid. | Diagnostic should remain disabled except during controlled staging tests.
Phase 1 - Bhoonidhi ResourceSat Completion | Source-aware raster/statistics contracts | Monitoring indexes; mask filter; image sources | Generalize Sentinel SCL assumptions to source-neutral masks, ResourceSat spectral roles, FCC display, and supported-index validation. | Hide unsupported indices; show mask provenance/provisional status; use FCC display mode for ResourceSat. | Source registry, ResourceSat band roles, mask asset, MSAVI formula, unsupported-index rejection, source-neutral pixel-count fields. | API/frontend contract tests for source-specific indices and mask fields. | Backend/API - Sanoj; Frontend - Rafiq | P0 | In Progress | ResourceSat supports NDVI, MSAVI, NDMI, NDWI_GREEN_NIR; NDRE/RECI hidden or rejected; output no longer exposes Sentinel-only SCL wording. | Complete source-neutral API/UI rename and tests. | Current working tree includes active ResourceSat/source-neutral changes.
Phase 1 - Bhoonidhi ResourceSat Completion | Single-scene COG preparation | Latest Image layer; monitoring date line | Prepare ResourceSat BOA products into analytic COG and Akasha-generated mask COG with correct band order and reflectance metadata. | No direct UI until loaded into catalog; later appears as selectable ResourceSat date. | prepare_resourcesat_liss3_boa_cogs.py, BAND_META parsing, mask classes, COG validation. | Synthetic and real-product COG tests; verify-manifest-cogs. | Fullstack - Deva; Backend/API - Sanoj | P0 | In Progress | Generated analytic has 4 bands; mask aligns; overviews valid; metadata records provisional mask method and attribution. | More real samples to validate consistent product layout. | Proceed with provisional mask fallback because diagnostic found no native quality layer.
Phase 1 - Bhoonidhi ResourceSat Completion | Full 60 km AOI composite | Image sources; date line; full coverage monitoring | Build ingestion-time cloud-free composite per dated window: one analytic COG plus one mask COG covering Bangalore 60 km AOI. | ResourceSat FCC overlay should cover the full launch AOI; timeline dates represent composite dates. | Composite grid, reprojection, valid-pixel selection, most-recent-valid tie-break, metrics, STAC item generation. | verify-composite requires coverage threshold, CRS/resolution, mask classes, COG overviews, catalog item. | Fullstack - Deva; Architect / Fullstack / DevOps - Nishanth | P0 | In Progress | Composite date renders without multi-scene errors; polygons anywhere in AOI return cloud-free stats. | Enough Online=Y products within compositing windows. | This is the launch gate before switching default source to ResourceSat.
Phase 1 - Bhoonidhi ResourceSat Completion | Scheduled sync and 90-day backfill | Date line; historical monitoring | Automate search, download, prepare, composite, verify, and ingest on the whitelisted staging VM. | Timeline lists available composite dates for the last 3 months. | bhoonidhi-sync, SQLite ledger, retry/backoff, raw/temp paths under /srv/akasha, STAC/MinIO ingest. | Idempotency tests, rate-limit handling tests, operator logs, daily schedule validation. | Architect / Fullstack / DevOps - Nishanth; Fullstack - Deva | P1 | In Progress | Re-running sync skips completed products, rebuilds affected composites, and avoids duplicates. | Bhoonidhi rate limits and daily download caps. | Backfill may need to span multiple days.
Phase 2 - Core EOS Monitoring Parity | Field analytics and charts | Monitoring; Charts; Vegetation indices; Details | Field-specific index statistics, trend chart, selected source/date/index, downloadable index/report outputs. | Field trend chart, index panel, cloud/mask controls, download menu. | Field analytics API, field exports, BFF statistics engine. | API and frontend tests for analytics/export flows. | Frontend - Rafiq; Backend/API - Sanoj | P0 | Partial | Selected field shows latest index stats/trends and exports; source-specific index availability enforced. | ResourceSat composite dates and source-neutral mask payloads. | EOS VMI/ReCI are not supported unless source data supports them.
Phase 2 - Core EOS Monitoring Parity | Map tools and layer controls | Find location; Zoom tool; Distance and area measurements; Split view; Layers; Contrast view | Map controls, coordinate readout, measurement, source/date panel, compare control, opacity and visibility. | Layer panel, compare control, measurement tool, command palette, legend, MapLayerManager. | Same-origin tile templates from BFF; no direct storage URLs. | Frontend tests for layer manager, compare, controls, measurement, URL state. | Frontend - Rafiq | P1 | Partial | User can inspect source/date layers and compare dates without disrupting basemap. | Polish split/contrast parity against exact client expectations. | EOS terminology may need client screenshot alignment.
Phase 3 - Seasonality & Field Manager | Season lifecycle | Seasonality: create, edit, delete season | Create/edit/delete seasons, assign fields to seasons, preserve at least one active season rule. | Season management UI and field assignment workflow. | Seasons API and field-season association already exist; enforce EOS deletion/transfer rules. | Tests for season duration edits and field association constraints. | Backend/API - Sanoj; Frontend - Rafiq | P1 | Partial | Season list supports create/edit/delete; fields are always associated with at least one season. | UI completion and EOS-specific validation rules. | Backend primitives exist; full EOS workflow needs UI hardening.
Phase 3 - Seasonality & Field Manager | Crop rotation, sowing and allocation | Field Manager: crop rotation, manage sowing, crop allocation | Capture crop type, variety, sowing/planting/harvest metadata, season crop allocation, and field filters. | Field edit forms and manager screens for crop/season assignment. | Plot/field metadata columns exist; add normalized crop catalog only if required. | Validation tests for dates inside season and crop allocation filters. | Frontend - Rafiq; Backend/API - Sanoj | P1 | Planned | Crop and sowing metadata drive monitoring filters and reports. | Client crop taxonomy, if different from free text. | Keep initial version lightweight unless client needs full crop catalog admin.
Phase 3 - Seasonality & Field Manager | Field groups | Field Manager: field groups | Group fields by operational characteristics for filtering, reports, weather and operations. | Field groups page with create/edit/delete and assign fields. | Field groups API and membership table already exist. | API/frontend tests for assignment and group filters. | Fullstack - Deva; Frontend - Rafiq | P1 | Partial | Groups can be maintained and reflected in field views/reports. | UI completion. | Backend is ahead of product UI.
Phase 4 - Operations & Scouting | Field activity log | Field Activity Log | Track planned/completed field work, inputs, status, assignee, cost, notes and CSV export. | Activity log page with filters and edit flows. | Activities API and CSV export already exist. | Tests cover list/create/update/delete/export. | Backend/API - Sanoj; Frontend - Rafiq | P1 | Partial | Activities can be created and exported; UI supports daily operations workflow. | UX parity for filters and status views. | Native Akasha data, not EOS import.
Phase 4 - Operations & Scouting | Scout tasks | Scouting: task description, report, download, closed tasks | Map-based scouting tasks with status, priority, assignee, notes, coordinates and closed-task handling. | Scout tasks page and map pins. | Scout task API exists; attachments model exists. | Tests for create/update/close/delete and future report/download. | Frontend - Rafiq; Backend/API - Sanoj | P1 | Partial | User can create and close scouting tasks for fields; reports/downloads are added after core task UI. | Attachment/report UX. | Current backend primitives exist.
Phase 5 - Reports, Leaderboard & Risk | Field leaderboard and reports | Overview: Season Analytics, Field Leaderboard, Custom Report | Rank fields by latest monitoring signals and export custom report templates. | Leaderboard and reporting pages; template UI. | Reports API, templates and leaderboard export routes exist. | CSV export tests and report-template API tests. | Frontend - Rafiq; Backend/API - Sanoj | P1 | Partial | Client can view ranked fields and export report data once analytics data is dense enough. | ResourceSat history and UI completion. | Reports should remain evidence-based.
Phase 5 - Reports, Leaderboard & Risk | Disease and pest risk context | Risks; Diseases & Pests | Transparent crop-risk context, not diagnosis from vegetation index alone. | Diseases & Pests page with evidence and disclaimers. | Risk API exists with transparent rule model. | Tests for risk summary route and unsupported cases. | Backend/API - Sanoj; Frontend - Rafiq | P2 | Partial | Risk explanations cite input data and avoid unsupported diagnosis. | Weather provider and validated crop-stage models for stronger alerts. | Do not overclaim disease/pest detection.
Phase 6 - Weather | Historical weather analytics | Historical weather; precipitation, temperature, active temperature, moisture charts | Field-level historical weather charts aligned to seasons and monitoring dates. | Weather analytics page with chart panels. | Weather provider adapter behind BFF; normalized field/date weather endpoints. | Provider contract tests and chart tests. | Fullstack - Deva; Frontend - Rafiq | P2 | Deferred | Historical precipitation/temperature/moisture charts render for selected fields. | Weather data provider selection and license. | No provider is selected yet.
Phase 6 - Weather | Weather forecast | Weather Forecast | Forecast cards and timeline for selected fields. | Forecast page with field cards and forecast timeline. | Forecast API normalized behind BFF. | Provider mocks and fallback-state tests. | Fullstack - Deva; Frontend - Rafiq | P2 | Deferred | Forecast data is available without exposing provider credentials. | Weather data provider. | Deferred until provider decision.
Phase 7 - Data Manager & Connections | Dataset uploads | Data Manager: Data | Upload and manage boundary/machinery datasets with metadata and validation messages. | Data manager page with upload/list/status. | Datasets API and uploaded_datasets table exist; extend parsers for target formats. | Upload validation tests and no-secret storage checks. | Fullstack - Deva; Frontend - Rafiq | P2 | Partial | User can upload supported datasets and see validation state. | Supported format list and file-size limits. | Current backend supports initial dataset metadata.
Phase 7 - Data Manager & Connections | Machinery connections | Data Manager: Connections | External machinery connection status and future OAuth integrations such as John Deere-style flows. | Connections page with disconnected/connected states. | Connection status API placeholder; no external OAuth until target integration confirmed. | Mock connection tests before live provider work. | Architect / Fullstack / DevOps - Nishanth; Fullstack - Deva | P3 | Deferred | Client-approved machinery provider can connect without leaking tokens. | Provider agreement, OAuth app, callback domain. | Do not build speculative OAuth integrations.
Phase 8 - VRA Maps | Vegetation zoning | Zoning; VRA maps | Create zones from selected index/date and field, with 2-7 zone support where appropriate. | Vegetation VRA page with zone count, detail level, preview and save. | Zoning algorithm over cloud-masked index rasters; persist map metadata. | Algorithm unit tests and export validation. | Fullstack - Deva; Frontend - Rafiq | P2 | Planned | Zones are reproducible and derived from selected source/date/index. | ResourceSat composite analytics ready. | Start with vegetation zones before fertilizer/seeding prescriptions.
Phase 8 - VRA Maps | Sowing, nitrogen, P&K and map builder | Create sowing maps; nitrogen fertilization; P&K; map builder; supported formats; save maps | Build variable-rate maps and exports using selected layers and optional uploaded machinery/yield data. | VRA module pages for sowing, vegetation, P&K, map builder, soil sampling. | Prescription model, export format support, layer combination pipeline. | Golden-file export tests and machinery-format compatibility tests. | Fullstack - Deva; Architect / Fullstack / DevOps - Nishanth | P3 | Planned | Saved VRA maps can be downloaded in agreed supported formats. | Client equipment/export-format requirements. | Map builder can use up to five selected layers after data manager exists.
Phase 9 - Production Hardening | Production Coolify rollout | Pilot operations | Create production environment, deploy validated Git SHA, run migrations/seeds, smoke, rollback rehearsal. | Production SPA with final domain/TLS. | Production Coolify stack, env, migrations, MinIO/STAC/PostGIS state. | Manual approval workflow, smoke tests, private-port scans, rollback. | Architect / Fullstack / DevOps - Nishanth; Team Lead - Karthi | P0 | Planned | Production deploy uses exact staging-validated image tag and passes authenticated smoke tests. | Production VM/domain/TLS/secrets. | Staging path is validated; production promotion remains planned.
Phase 9 - Production Hardening | Monitoring, backup and support | Operational readiness | Monitor latest composite freshness, Bhoonidhi failures, MinIO usage, STAC registration, backups and restore drills. | Admin/support visibility where needed. | Worker logs, support bundle, backup/restore scripts, ingestion ledger, stale-date alerts. | Restore dry run, support-bundle redaction, alert checks. | Architect / Fullstack / DevOps - Nishanth; Team Lead - Karthi | P1 | Planned | Operators can diagnose failed refreshes and restore from backup. | Production backup target and alert channel. | Required before long-running pilot.

## Built Inventory
Area | Implemented / Validated Capability | Status | Evidence | Owner | Next Gap
Architecture | Canonical multi-service topology with web gateway, API, TiTiler, STAC API, PostGIS, MinIO, ingestion worker. | Done | README, infra/docker, infra/gateway, apps/api, services/*. | Architect / Fullstack / DevOps - Nishanth | Production environment creation.
Frontend | React 18 + Vite + TypeScript SPA, product shell, authenticated routes, MapPage field analytics workspace. | Done | apps/frontend/src/routes/ProductRoutes.tsx; FieldAnalyticsPage uses MapPage. | Frontend - Rafiq | Complete placeholder modules.
Basemap | ArcGIS/Esri basemap configured as visual base layer. | Done | apps/frontend package uses @esri/maplibre-arcgis; /api/config basemap payload. | Frontend - Rafiq | Keep ResourceSat as overlay only.
Map UX | Layer panel, source/date selection, opacity, visibility, compare, measure, command palette, legend, URL state. | Done | apps/frontend/src/components/map and components/layers tests. | Frontend - Rafiq | EOS split/contrast polish.
BFF Product API | Config, sources, dates, default layer, display-mode tiles, index statistics. | Done | apps/api/app/product.py. | Backend/API - Sanoj | Finish source-neutral ResourceSat fields.
Raster Statistics | BFF computes cloud/mask-aware index stats; TiTiler serves display tiles only. | Done | apps/api/app/raster/service.py and statistics_core.py. | Backend/API - Sanoj | ResourceSat composite statistics smoke.
Auth/Teams | Cookie sessions, team RBAC, login/logout/bootstrap/password, API keys, notifications. | Done | apps/api/app/auth*.py, account.py, models.py. | Backend/API - Sanoj | Production user provisioning policy.
Fields/Plots | Plot CRUD, field CRUD, field groups, seasons, GeoJSON import/export. | Partial | apps/api/app/plots.py, fields.py, field_groups.py, seasons.py. | Backend/API - Sanoj; Frontend - Rafiq | Full EOS upload formats and season UI.
Operations | Activities, scout tasks, attachments model, activity CSV export. | Partial | apps/api/app/operations.py, scout_tasks.py, models.py. | Backend/API - Sanoj; Frontend - Rafiq | Complete operations/scouting UI parity.
Reports/Risk | Report templates, leaderboard APIs, risk summary API. | Partial | apps/api/app/reports.py, risk.py. | Backend/API - Sanoj | UI polish and data density.
Data Manager | Dataset upload metadata and connection status endpoints. | Partial | apps/api/app/data_manager.py. | Fullstack - Deva; Frontend - Rafiq | Format parsers and UI completion.
Bhoonidhi Diagnostics | Real staging auth/search/download/inspect validated on 2026-06-14. | Validated | docs/impl-plan/feature-bhoonidhi-diagnostic-download-1.md. | Backend/API - Sanoj; Architect / Fullstack / DevOps - Nishanth | Full ingestion/composite path.
ResourceSat Registry | ResourceSat LISS-3 BOA source, FCC display mode, spectral roles, provisional mask metadata. | In Progress | apps/api/app/raster/catalog_resolver.py and indices.py. | Backend/API - Sanoj | Complete source-neutral payload migration.
Composite Pipeline | Best-available-pixel ResourceSat composite helpers, verify-composite, bhoonidhi-sync ledger. | In Progress | services/ingestion/akasha_ingest/composite.py, sync.py, worker.py. | Fullstack - Deva; Architect / Fullstack / DevOps - Nishanth | Real full-AOI composite smoke.
CI/CD | CI workflow, Trivy scan, GHCR image build, Coolify staging patch/deploy, production deploy workflow. | Validated | .github/workflows/*.yml; infra/selfhosted/README.md. | Architect / Fullstack / DevOps - Nishanth | Production promotion and rollback drill.

## EOS Feature Mapping
EOSDA Module | Baseline Functionalities | Akasha Current Status | Current Akasha Coverage | Gap / Planned Work | Owner | Priority
Seasonality | Create season; edit season; delete season; copy/transfer fields; season dates drive analytics. | Partial | Backend seasons and field-season schema exist. | Complete season UI, copy/transfer workflow, deletion guardrails. | Backend/API - Sanoj; Frontend - Rafiq | P1
Add Field | Upload fields; draw field; upload error handling; layers/latest image during field creation. | Partial | Draw/edit with Terra Draw and GeoJSON import/export exist. | Add SHP/KML/KMZ upload, parameter mapping, upload manager, circle/cut tools if required. | Frontend - Rafiq; Backend/API - Sanoj | P1
Monitoring | Image sources, elevation/slope, date line, crop info, crop rotation, growth stages, risks, charts. | Partial | Source/date overlays, field analytics, risk API, trend chart foundations exist. | ResourceSat composites, season-aware charts, elevation/slope if required. | Frontend - Rafiq; Backend/API - Sanoj | P0
Monitoring Indexes | NDVI, NDRE, MSAVI, ReCI, NDMI, details, download, mask filter. | Partial | NDVI, NDRE, NDMI, NDWI and MSAVI registry; exports and mask controls exist. | Hide unsupported indices per source; ResourceSat does not support NDRE/ReCI. | Backend/API - Sanoj | P0
Weather | Historical weather, precipitation, daily temperatures, active temperature, forecast. | Deferred | Weather routes are placeholder-only. | Select provider, implement BFF adapter and UI charts. | Fullstack - Deva; Frontend - Rafiq | P2
Scouting | Task description, general info, report, download, closed tasks. | Partial | Scout task API exists; UI route exists. | Map pins, reports/downloads, closed-task UX. | Frontend - Rafiq; Backend/API - Sanoj | P1
Overview | Season analytics, field leaderboard, custom report. | Partial | Leaderboard/report APIs and templates exist. | Client-ready UI, report builder, season analytics from dense data. | Frontend - Rafiq; Backend/API - Sanoj | P1
VRA Maps | Sowing, nitrogen, P&K, map builder, savings, machinery formats, save maps. | Planned | Navigation shell exists. | Zoning, prescriptions, layer combination, equipment-format exports. | Fullstack - Deva; Architect / Fullstack / DevOps - Nishanth | P2
Field Activity Log | Track and manage field operations. | Partial | Activity API and export exist. | Complete operations UI and filters. | Frontend - Rafiq; Backend/API - Sanoj | P1
Data Manager - Data | Upload/manage field datasets. | Partial | Dataset upload metadata API exists. | UI, validation reports, supported file parsers. | Fullstack - Deva; Frontend - Rafiq | P2
Data Manager - Connections | External machinery/data connections. | Deferred | Connection status placeholder exists. | Provider-specific OAuth after client confirms target integration. | Architect / Fullstack / DevOps - Nishanth; Fullstack - Deva | P3
Field Manager | Crop rotation, manage sowing, crop allocation, field groups. | Partial | Field groups and metadata primitives exist. | Complete crop/season allocation UI and rules. | Frontend - Rafiq; Backend/API - Sanoj | P1
Team Management | Add users, roles, dashboard, edit/switch teams. | Partial | Team memberships and roles exist; account/team endpoints exist. | Team admin UI and invitation/user-management workflow. | Backend/API - Sanoj; Frontend - Rafiq | P2
Settings | Account/product settings. | Partial | Account settings/API key routes and pages exist. | Finalize settings UI, notification preferences, team controls. | Frontend - Rafiq; Backend/API - Sanoj | P2
Access Through API | API access for integrations. | Partial | API key metadata/create/revoke exists. | Document external API surface and rate-limit policy. | Backend/API - Sanoj; Architect / Fullstack / DevOps - Nishanth | P2

## Bhoonidhi ResourceSat Plan
Workstream | Task | Status | Owner | Acceptance Criteria | Dependencies / Notes
Validated access | Staging diagnostic endpoint, auth/search/download/inspect real LISS-3 BOA product. | Validated | Backend/API - Sanoj; Architect / Fullstack / DevOps - Nishanth | Real product downloaded from egress 20.219.3.35; four bands readable; no native mask found. | Keep diagnostics disabled outside controlled staging tests.
Source contracts | ResourceSat source metadata, FCC default display, role-based indices, source-neutral mask fields. | In Progress | Backend/API - Sanoj | Source lists supported indices and display modes; unsupported index requests fail safely. | Frontend/API type migration still active.
Single-scene prep | BAND_META parsing, analytic.tif and mask.tif generation, COG validation. | In Progress | Fullstack - Deva; Backend/API - Sanoj | 4-band analytic + 1-band mask aligned, overviews valid, reflectance scale/offset correct. | Validate additional real products.
Composite build | Full 60 km AOI ingestion-time cloud-free composite. | In Progress | Fullstack - Deva; Architect / Fullstack / DevOps - Nishanth | One dated analytic+mask pair covers launch AOI and avoids query-time mosaic errors. | Availability of enough Online=Y scenes.
Catalog/storage | Upload composite COGs to MinIO and register dated composite STAC item. | In Progress | Fullstack - Deva | BFF /sources/{id}/dates lists composite dates with metrics and tileAvailable true. | STAC/MinIO env and catalog migration health.
Scheduled sync | bhoonidhi-sync with SQLite ledger, retries, idempotent product selection and composite rebuild. | In Progress | Architect / Fullstack / DevOps - Nishanth | Re-running sync skips terminal products and logs retryable failures. | Bhoonidhi rate limits; /srv/akasha disk use.
UI timeline | Past-three-month composite date timeline, latest cloud-free default, FCC overlay attribution. | Planned | Frontend - Rafiq | User selects composite date and sees FCC overlay plus cloud-free stats. | Composite dates in catalog.
Production switch | Switch default source from Sentinel to ResourceSat after composite smoke. | Planned | Architect / Fullstack / DevOps - Nishanth; Team Lead - Karthi | ResourceSat is default; Sentinel removed or hidden from production. | Only after Phase 2b full-AOI smoke succeeds.

## Risks & Decisions
Type | Decision / Risk / Input | Status | Owner | Action / Note
Locked decision | ArcGIS remains the true-colour basemap; ResourceSat FCC is an Akasha overlay. | Locked | Team Lead - Karthi | Do not replace basemap with ResourceSat.
Locked decision | ResourceSat LISS-3 has no blue band; default display is FCC NIR/Red/Green. | Locked | Backend/API - Sanoj | Do not fake natural colour.
Locked decision | Full 60 km AOI coverage is required for launch via ingestion-time composite. | Locked | Architect / Fullstack / DevOps - Nishanth | Avoid query-time mosaic as the launch path.
Locked decision | No native quality/cloud raster found in validated product; use Akasha threshold mask v1. | Locked | Backend/API - Sanoj | Label as provisional in API/UI.
Risk | Bhoonidhi rate limits and daily download throttling can slow 90-day backfill. | Open | Architect / Fullstack / DevOps - Nishanth | Spread backfill across days and reuse tokens.
Risk | ResourceSat product availability may not yield cloud-free full coverage in every window. | Open | Fullstack - Deva | Composite metrics must show coverage and freshness honestly.
External input | Weather provider and license are not selected. | Needed | Team Lead - Karthi | Required before Weather phase implementation.
External input | Client equipment/export formats for VRA are not confirmed. | Needed | Team Lead - Karthi | Required before VRA export implementation.
External input | Production domain, TLS, secrets, and Coolify production service UUID. | Needed | Architect / Fullstack / DevOps - Nishanth | Required for production cutover.
Non-goal | Do not expose Bhoonidhi, MinIO, STAC, TiTiler or raw object URLs to the browser. | Always | Architect / Fullstack / DevOps - Nishanth | Keep one-public-service rule.
Non-goal | Do not claim disease/pest diagnosis from vegetation index alone. | Always | Backend/API - Sanoj | Risk model must be evidence-bound.